## Sheet1
Timeline
Development | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Research | bar: Week 1; Week 3; Week 6
Project Setup | bar: Week 2
Neural Network NEAT Implementation | bar: Week 3 to Week 4
Neural Network Integration | bar: Week 4 to Week 5
Neural Network Data Display | bar: Week 5 to Week 6
Testing & Neural Network Tuning | bar: Week 7 to Week 8
Polish | bar: Week 9 to Week 10